## Sheet1
Title | Status | Assignees | Type | Repository | Priority | Start Date | Target Date | URL
[Backend] Database migration sesuai schema MySQL | Done | Fajar1180 | Issue | radenelsa7-bot/PM_UAS_rekayasa_Sistem_Informasi | P2 | 2026-05-22 | 2026-05-22 | https://github.com/radenelsa7-bot/PM_UAS_rekayasa_Sistem_Informasi/issues/12
[Frontend] Setup Flutter project & struktur folder | Backlog | tetepsafarudin | Issue | radenelsa7-bot/PM_UAS_rekayasa_Sistem_Informasi | - | - | - | https://github.com/radenelsa7-bot/PM_UAS_rekayasa_Sistem_Informasi/issues/13
Project Management dan Penugasan Tim: Backend, Frontend, dan Testing | Done | radenelsa7-bot | Issue | radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak | - | - | - | https://github.com/radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak/issues/1
[PM] Finalisasi SRS & distribusi dokumen ke tim | Done | radenelsa7-bot | Issue | radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak | - | - | - | https://github.com/radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak/issues/3
[PM] Setup GitHub Project Board & milestone tracking | Done | radenelsa7-bot | Issue | radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak | - | - | - | https://github.com/radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak/issues/4
[PM] Buat WBS & jadwal detail per anggota | Done | radenelsa7-bot | Issue | radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak | - | - | - | https://github.com/radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak/issues/5
[Frontend] Desain wireframe & UI kit (Figma) | In progress | tetepsafarudin | Issue | radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak | - | - | - | https://github.com/radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak/issues/9
[Testing] Buat Test Plan dokumen | Done | NabilahAsana | Issue | radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak | - | - | - | https://github.com/radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak/issues/10
[Backend] API Auth: Register, Login, Logout (FR-01, FR-02, FR-03) | In progress | Fajar1180 | Issue | radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak | P1 | - | - | https://github.com/radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak/issues/11
[Backend] API Service Catalog: Categories & Provider List (FR-08, FR-09, FR-10) | In progress | Fajar1180 | Issue | radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak | P1 | - | - | https://github.com/radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak/issues/12
[Backend] Model & Eloquent Relationships | In progress | Fajar1180 | Issue | radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak | - | - | - | https://github.com/radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak/issues/13
[Frontend] Screen: Login & Register | In progress | faznalaisal44 | Issue | radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak | - | - | - | https://github.com/radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak/issues/14
[Frontend] Screen: Home & Daftar Kategori | In progress | faznalaisal44 | Issue | radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak | - | - | - | https://github.com/radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak/issues/15
[Frontend] Screen: Daftar Provider & Detail Provider | In progress | faznalaisal44 | Issue | radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak | - | - | - | https://github.com/radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak/issues/16
[Testing] Testing Auth & Service Catalog API (Postman) | In progress | faznalaisal44 | Issue | radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak | - | - | - | https://github.com/radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak/issues/17
[Backend] API Orders: CRUD & Status Lifecycle (FR-11 s/d FR-14) | Ready | Fajar1180 | Issue | radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak | - | - | - | https://github.com/radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak/issues/18
[Backend] Auto-create DP Payment saat Order dibuat (BR-01) | Ready | NabilahAsana | Issue | radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak | - | - | - | https://github.com/radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak/issues/19
[Backend] API Reviews & Rating (FR-23, FR-24) | Ready | Fatinasy7 | Issue | radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak | - | - | - | https://github.com/radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak/issues/20
[Frontend] Screen: Form Buat Order | Ready | faznalaisal44 | Issue | radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak | - | - | - | https://github.com/radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak/issues/21
[Frontend] Screen: Detail Order & Riwayat Order | Ready | faznalaisal44 | Issue | radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak | - | - | - | https://github.com/radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak/issues/22
[Frontend] Screen: Provider – Terima/Tolak & Mulai Order | Ready | tetepsafarudin | Issue | radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak | - | - | - | https://github.com/radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak/issues/23
[Testing] Testing Order Lifecycle (Postman + Manual) | Ready | faznalaisal44 | Issue | radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak | - | - | - | https://github.com/radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak/issues/24
[PM] Review progress Week 2 & koordinasi Week 3 | Done | radenelsa7-bot | Issue | radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak | - | - | - | https://github.com/radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak/issues/25
[Backend] Integrasi Payment Gateway QRIS – Generate QR (FR-16, FR-19) | Ready | Fajar1180 | Issue | radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak | - | - | - | https://github.com/radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak/issues/26
[Backend] Webhook Payment Callback & Status Update (FR-17, FR-20) | Ready | NabilahAsana | Issue | radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak | - | - | - | https://github.com/radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak/issues/27
[Backend] Integrasi n8n – Event Notifikasi (FR-21, FR-22) | Ready | Fatinasy7 | Issue | radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak | - | - | - | https://github.com/radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak/issues/28
[Frontend] Screen: Pembayaran DP (QRIS) | Ready | tetepsafarudin | Issue | radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak | - | - | - | https://github.com/radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak/issues/29
[Frontend] Screen: Pembayaran Pelunasan (QRIS Final) | Ready | tetepsafarudin | Issue | radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak | - | - | - | https://github.com/radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak/issues/30
[Frontend] Screen: Rating & Review + Dashboard Admin/Treasurer | Ready | tetepsafarudin | Issue | radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak | - | - | - | https://github.com/radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak/issues/31
[Testing] Testing Payment Flow & Webhook | Ready | Fajar1180 | Issue | radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak | P0 | - | - | https://github.com/radenelsa7-bot/PM_uts_praktikum_pemograman_aplikasi_bergerak/issues/32